



CDC

H1N1 Vaccination Campaign

Planning Checklist

8/1/09

	Note:
	This is a DRAFT document. The final version will be posted at CDC H1N1 Vaccine planning web page in the near future.



	
	

	Introduction:

	This document is intended for state and local planners. Its purpose is to outline main planning actions. It is not meant to be exhaustive and additional more detailed guidance is or will be available on specific topics. Within each state, the checklist should be tailored to distinguish state and local responsibilities.  



	
	

	
	

	General:

	 FORMCHECKBOX 
  
	Ensure clear delineation of responsibilities and regular communication between involved programs at state level (Preparedness, Immunization, others)

	
	 FORMCHECKBOX 

	Clear delineation of responsibilities and regular communication between state and local programs



	
	
	

	Target and Priority Groups:
	 FORMCHECKBOX 

	Determine estimated size in jurisdiction of target and priority groups as defined by ACIP (http://www.cdc.gov/h1n1flu/vaccination/acip.htm).


	
	 FORMCHECKBOX 

	Develop plans which may include public health sponsored clinics or vaccination via private sector vaccinators to reach each target and priority group.


	
	
	

	Vaccination by Private Sector Partners:
	 FORMCHECKBOX 

	Meet with and disseminate information through medical societies, hospital associations, healthcare provider professional organizations



	
	 FORMCHECKBOX 

	Conduct mail outs or blast fax information to lists of providers obtained from licensing boards or medical societies



	
	 FORMCHECKBOX 

	Identify clinical providers and health systems interested in providing H1N1 vaccine (e.g. pediatricians, including non-VFC providers, family physicians, Obstetrician/Gynecologists, internists, HMOs, hospitals and other health care facilities)



	
	 FORMCHECKBOX 

	Identify community immunizers interested in administering H1N1 vaccine



	
	 FORMCHECKBOX 

	Develop a  pre-registration process so providers can indicate interest, receive information updates as available, and provide information needed for vaccine delivery



	
	 FORMCHECKBOX 

	Provide easily-locatable information on health department website for vaccinators, indicating what role they might play in given state/jurisdiction and how they can obtain information



	
	 FORMCHECKBOX 

	Use federal language, once available, to develop provider agreement between providers and public health



	
	 FORMCHECKBOX 

	Contact large businesses regarding plans for worksite vaccinations



	
	 FORMCHECKBOX 

	Contact college and university health centers


	
	
	

	Vaccination by Other Partners:
	
	Collaborate with the following systems and facilities, where applicable, as above to ensure vaccination of populations served or associated with them:

	
	
	 FORMCHECKBOX 

	Military bases to develop plan for military dependants

	
	
	 FORMCHECKBOX 

	VA clinics

	
	
	 FORMCHECKBOX 

	IHS clinics and tribal clinics

	
	
	 FORMCHECKBOX 

	FQHCs and RHCs (including reaching out to state Primary Care office and Primary Care Association)


	
	
	

	Public Health Vaccination Clinics:
	Clinics that are conducted, organized, or sponsored by public health.


	
	 FORMCHECKBOX 

	Determine populations that will be targeted for vaccination via large scale/public health sponsored clinics



	
	 FORMCHECKBOX 

	Identify clinic sites (number, locations, points of contact, alternative sites, accessibility)

	
	 FORMCHECKBOX 

	Estimate size and type (target and priority groups) of population to be served per site



	
	 FORMCHECKBOX 

	Determine staffing needs, and sources of staffing



	
	 FORMCHECKBOX 

	Develop plans for staffing, including identification of sources of volunteers and development of MOAs with relevant organizations.



	
	 FORMCHECKBOX 

	Initiate contracts with personnel agencies or community vaccinators to provide staff or organize/conduct clinic



	
	 FORMCHECKBOX 

	Define process to allow healthcare workers from other jurisdictions to vaccinate if necessary



	
	
	

	Coordination of Vaccine Distribution:

	 FORMCHECKBOX 

	Determine overall relative allocations for public health clinics, including school-located vaccination, clinical providers, and other private sector providers (e.g. community immunizers, retail providers)



	
	 FORMCHECKBOX 

	As part of pre-registration or registration process, collect number of influenza doses administered previous year, where applicable, to help determine provider capacity for administering influenza vaccine



	
	 FORMCHECKBOX 

	Determine plan for allocating vaccine (e.g. partial shipments to all providers, sequential shipments to sets of providers)



	
	 FORMCHECKBOX 

	Develop staffing plan for entry of data into VACMAN



	
	 FORMCHECKBOX 

	Develop plan for provider practices unable to accommodate minimum shipment size (internal distribution, limiting vaccine to larger sites)



	
	 FORMCHECKBOX 

	Develop plan for tracking vaccine usage by vaccinators to ensure vaccine supply is adequately directed where needed. 



	
	
	

	Vaccination of Healthcare Workers and EMS:

	 FORMCHECKBOX 

 FORMCHECKBOX 

	Develop agreements with hospitals to delegate responsibility for vaccination of staff, and determine size of staff (total and staff with direct patient contact).

Collect required information (e.g. shipping address, contact persons, etc.) for vaccine delivery



	
	 FORMCHECKBOX 

	Develop plan for outpatient providers (e.g. they may receive vaccine directly through centralized distribution, or if not among the first to receive vaccine may pick up at defined location)



	
	 FORMCHECKBOX 

	Develop plan for vaccinating EMS 



	
	
	

	Vaccination of School-aged Children:

	 FORMCHECKBOX 

 FORMCHECKBOX 

	Make connections with education partners at state level

Make connections with education partners, including school districts, at local level; create a list of schools/school districts willing to participate in school-located clinics



	
	 FORMCHECKBOX 

	Develop plans for staffing school-located clinics, including identification of sources of volunteers and development of MOAs with relevant organizations



	
	 FORMCHECKBOX 

	Develop informational materials for parents 



	
	 FORMCHECKBOX 

	Work with local legal advisors to design consent forms



	
	 FORMCHECKBOX 

	Develop plans to distribute and maximize return of consent forms where applicable (i.e., if school clinics during school hours and without parents present are planned)



	
	 FORMCHECKBOX 

	Ensure VIS is provided to parents for each vaccination dose



	
	 FORMCHECKBOX 

	Develop plan to inform and obtain support of principals, teachers, and parent organizations



	
	 FORMCHECKBOX 

	Develop plan for informing and obtaining support from physicians in the community about school-located vaccination



	
	
	

	Tribal Populations:

	 FORMCHECKBOX 

	Include IHS and tribal planners in finalizing vaccinations plans



	
	 FORMCHECKBOX 

	Ensure tribal populations are included in state vaccine allocation plans



	
	
	

	Hard-to-reach and Vulnerable Populations:
	 FORMCHECKBOX 

 FORMCHECKBOX 

	Define hard to reach populations
Estimate size of populations



	
	 FORMCHECKBOX 

	Develop plan for reaching these populations and/or transporting to clinic sites



	
	 FORMCHECKBOX 

	Develop MOAs with public agencies, volunteer organizations, and others to reach these populations



	
	
	

	Communications:

	 FORMCHECKBOX 

	Ensure clear communication about implementation of target and priority group recommendations and need for second dose 



	
	 FORMCHECKBOX 

	Identify the varied audiences that need to receive audience-specific vaccine, vaccination, and vaccination site information and instructions



	
	 FORMCHECKBOX 

	Involve local stakeholders and/or key audience liaisons in shaping outreach strategies



	
	 FORMCHECKBOX 

	Identify language and cultural barriers and plan for addressing



	
	 FORMCHECKBOX 

	Plan testing of messages for receptivity, understanding.



	
	 FORMCHECKBOX 

	Create MOAs with channels for communication (e.g., print media/local papers, community and social or religious networks, commerce or local business partners



	
	 FORMCHECKBOX 

	Determine best means for targeting communication broadly to different ethnic and socioeconomic populations (Media, clinician outreach, websites or new media)



	
	 FORMCHECKBOX 

	Reach out to widely diverse local partners, volunteer groups and other NGOs with specific instructions and technical support on how to help disseminate messages and aid the general public in accessing vaccination sites.



	
	 FORMCHECKBOX 

	Plan information communication network throughout agencies at state and local levels to ensure coordination of messages



	
	 FORMCHECKBOX 

	Conduct ongoing assessment of strategies, and adjust messages as needed.



	
	
	

	Large Scale Clinic Planning:
	See guidelines at http://www.cdc.gov/h1n1/vaccination

	
	General:

	
	 FORMCHECKBOX 

	Determine cold storage status at site 



	
	 FORMCHECKBOX 

	Determine status of communications equipment



	
	 FORMCHECKBOX 

	Develop procedure for receiving and accounting for vaccine



	
	 FORMCHECKBOX 

	Develop site layout, patient flow, job descriptions, equipment needs



	
	 FORMCHECKBOX 

	Develop plan to provide ID to clinic staff



	
	 FORMCHECKBOX 

	Develop plan for responding to medical emergencies or adverse events (e.g. fainting)



	
	 FORMCHECKBOX 

	Develop plan for data collection



	
	 FORMCHECKBOX 

	Develop process for vaccination of non-English speakers (identify language needs and needed staffing)



	
	 FORMCHECKBOX 

	Ensure information on return date for second dose is provided



	
	 FORMCHECKBOX 

	Contact information for staff updated and available



	
	 FORMCHECKBOX 

	Training materials developed, including just in time training plan



	
	 FORMCHECKBOX 

	Contingency plans in the event of absenteeism



	
	 FORMCHECKBOX 

	Develop plan for advertising clinics to public and potential vaccinators 



	
	School-located Clinics:

	
	 FORMCHECKBOX 

	Address issues specific to vaccination of children (flow from classroom to vaccination)

	
	 FORMCHECKBOX 

	Plan for consent related issues at time of clinic (verifying identity of consented child when parent is not present)



	
	
	

	Doses Administered Tracking:

	 FORMCHECKBOX 

 FORMCHECKBOX 

	Determine data collection system and method for reporting minimum required data elements 

Define local data collection needs


	
	 FORMCHECKBOX 

	Distribute educational materials to vaccine administration sites



	
	 FORMCHECKBOX 

	Develop staffing plan and training for data collection, entering and forwarding at public clinics and at local and state health departments



	
	 FORMCHECKBOX 

	Determine equipment needs at all data collection and forwarding sites.



	
	
	

	Safety Monitoring:


	 FORMCHECKBOX 

 FORMCHECKBOX 

	Disseminate information to vaccinators on VAERS reporting

Operational statewide network to provide technical information and technical aid to and to receive notification of adverse events from healthcare providers

	
	 FORMCHECKBOX 

	Plan use of vaccinee card (may be provided by CDC) with data of vaccination, 1st dose/2nd dose, lot number, return date for 2nd dose, VAERS information 



	
	
	

	Legal:

	 FORMCHECKBOX 

	Contact primary public health counsel to determine which allied health professionals are legally permitted to administer vaccine, to what types of patients, and under what conditions.



	
	 FORMCHECKBOX 

	Ensure dissemination/explanation of PREP Act information



	
	
	


	For state and local jurisdictions where at least some vaccine will be shipped to a central receiving site and repackaged for shipping to other sites/providers:



	
	
	

	General:


	 FORMCHECKBOX 

	Develop system to track inventory from receiving site to further points of distribution to be able to replenish supply in timely manner 



	
	
	

	Vaccine Receiving Sites:

	 FORMCHECKBOX 

 FORMCHECKBOX 

	Staff responsibilities with respect to vaccine receipt defined.
Staff needs for receiving, storing, breakdown, repackaging calculated (taking into account absenteeism)


	
	 FORMCHECKBOX 

	Training materials developed



	
	
	

	Storage and Handling:

	 FORMCHECKBOX 

	Ensure adequate storage space for both refrigerated (preloaded syringes and multi-dose vials of vaccine and possibly, adjuvant) and non-refrigerated supplies 



	
	
	

	Transportation:

	 FORMCHECKBOX 

	Plan for transporting vaccine from receiving site o distribution sites



	
	 FORMCHECKBOX 

	Contingency plan for transportation



	
	 FORMCHECKBOX 

	Source and number of transportation staff identified (taking into account absenteeism)



	
	 FORMCHECKBOX 

	Training materials developed.



	
	
	

	Security:

	 FORMCHECKBOX 

	Security at receiving sites, in transport to administration sites, and at administration site



	
	 FORMCHECKBOX 

	Contingency plan in place for unexpected disruption at administration site



	
	 FORMCHECKBOX 

	Staffing for security identified



	
	 FORMCHECKBOX 

	Training materials developed




Page 1 of 6
DRAFT:  August 2009


